## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone: Complete tablet installtion
Create contracts with vendors |  |  |  | 1
Order tablets | Could have shipping delays of 2-3 days, and possibly some defective tablets that need to be replaced, older models are shipping from out of state, adding to the delays. The newer updated models are delayed oerseas due to storms |  |  | 14
Electrician installs wiring for tablets | 2 half days at each location to avoid closing for a day, check with electrician to see if mornings or afternoons are better |  |  | 4
Install tablets in the bar areas at the Downtown and North resaurant locations. |  |  |  | 3
Possible software upgrade |  |  |  | 3
Integrate tablets with POS software |  |  |  | 3
Milestone: Marketing Promotion
Connect the Sauce & Spoon marketing team with Terrific Tablets for branding |  |  |  | 2
Connect with marketing team to design table signs and email blasts |  |  |  | 2
Implement an email sign up |  |  |  | 1
Generate an email list |  |  |  | 2
Make a promotional for the table menu tablet pilot via table signs and email blasts | Create messaging about payment portal security to display on the tablets |  |  | 2
Revamp the menu items and coupons for mock-ups |  |  |  | 10
Upload mock-up menu and coupons to tablets |  |  |  | 0.5
Implement a post-dining survey to assess customer satisfaction |  |  |  | 2
Finalize tablet design and identify any gaps |  |  |  | 2
Test all tablets for hardward, software, and payment bugs in a non-live environment |  |  |  | 1
Milestone: Complete training
Preparations for all training (pre-training, manager training, and staff training) |  |  |  | 7
Schedule a training for a small group of managers |  |  |  | 0.5
create training program for managers |  |  |  | 3
Schedule meetings with the GM to discuss anything that could affect waitstaff tips |  |  |  | 0.5
Have small team meetings with waitstaff to address concerns | 1 hour at each location plus drive time |  |  | 0.5
Implement training manual for staff | Create a procedure for securing tablets at the end of the night (at the table or in a safe), Include payment security talking points in waitstaff training, Train staff to update menu in real time |  |  | 3
Milestone: Plan a soft launch | There will be a 4 hour session at each location |  |  | 1
Plan a soft launch day
Marketing team write up a promo for soft launch |  |  |  | 3
Invite friends and family to do a test run of the tablets. |  |  |  | 1
Have soft launch |  |  |  | 0.5
Schedule a follow up training for all waitstaff at each location |  |  |  | 1
Milestone: Tablet Launch | 2.5 hours at each location plus drive times |  |  | 1
Create a launch day plan: staffing, troubleshooting, etc

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: Schedule with an electrian
Contracts and Procurements
Create contracts and statement of work for vendors
Select a vendor
Procure Tablets
Connect Sauce and Spoon marketing team with Terrific Tablet for branding
Hiring IT Experts
Hire Web Designers
Hire programmers
Hire QA Tester
Genarate codes and software
Schedule photograhing of the various menus
Install the software unto the tablets
Test the application software
Upload menu photographs
Integrate tablets with POS software
Milestone:Install the tablets onto the tables in the bar areas of North and Downtown
Implement post-dinning surveys to assess customer satisfaction
Create push notifications
Update the system with PCI security standards
Complete Training
schedule training with management
Train management
Schedule a meeting with the kitchen staff through their GM
Train FOH and BOH by the managers
Test the tablet rollout at the various locations by staff
Launch the pilot rollout
Create launch day plan
Milestone: Have a test run with family and friends to mimic full service

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Push notifications | https://www.upmenu.com/software-for-restaurants/mobile-applications/tablet | 07/22/2021 | Push notifications to customers Push messages are 7 times more effective than email campaigns. With a tablet ordering system you can notify customers about promotions and increase your profits
Payment system | https://www.partech.com/blog/implementing-tablet-pos-into-your-restaurant/ | 07/22/2021 | Customers can order food or drink and make payment instantly
PCI security standards | https://pointofsale.com/how-tableside-ordering-can-help-your-restaurant/ | 07/26/2021

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Faster, More Efficient Experience | Average ticket time—the amount of time between sending an order and delivering it to the table | How long did it take for your appetizers to arrive? How long did it take for your mains to arrive? Have you visited before? Did the tablets increase or decrease your wait time? | time in minutes; good average is eight minutes for appetizers and 12-15 minutes for entrees. Total less than 30mins. | FALSE
Faster, More Efficient Experience | Online delivery checkout system | How was your experience with the online check out? How long did it take for the online checkout? On the scale of 1-5,do yo agreed that the online checkout was easier than human interactions? | Time in minutes; one-minute checkout time | FALSE
Customer Satisfaction | Technical issues Rate; | Doe the tablest work as expected? Were there unintended issues with the tablets? Are customers havign a better time witht he tablet? | average rate of technical issues reported by customers be less than 5% in the first six months. | FALSE
Customer Satisfaction | Lowered No of Incorrect orders | Were your orders accurate? How many rejected orders were there in the past week? | 100% order accuracy | FALSE
Customer Satisfaction | Wait Time in Lobby | How long was your wait in the lobby? HOw would you rate your wait in the lobby? | Time in minutes; ten minute-or-less wait time for a table, because of the decreased table turn time. | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
average table turn time be 30 minutes | how can we improve and are there unintended outcomes? | table turn time | how long did the customer take to order using the tablet? | Scaled | 1. no time at all | 2. less than two minutes | 3. around five minutes | 4. 5-10 minutes | 5. more than 10 minutes
|  |  | did the customer experience any delays in service? | Yes/No | YES | NO
|  |  | how long did the customer customer spent at the table? | Multiple choice | 1. less than 15 minutes | 2. 15-30 minutes | 3. more than 30 minutes
|  |  | how would the customer rate the ease of using tablets to place your orders? | Scaled | 1. very easy | 2. somewhat easy | 3. neither easy nor difficult | 4. somewhat difficult | 5. very difficult
|  |  | would you return again this month? | Yes/No | YES | NO | MAYBE
average table turn time be 30 minutes | how can we improve and are there unintended outcomes? | table turn time | how long did the customer take to order using the tablet? | Scaled | 1. no time at all | 2. less than two minutes | 3. around five minutes | 4. 5-10 minutes | 5. more than 10 minutes
|  |  | did the customer experience any delays in service? | Yes/No | YES | NO
|  |  | how long did the customer customer spent at the table? | Multiple choice | 1. less than 15 minutes | 2. 15-30 minutes | 3. more than 30 minutes
|  |  | how would the customer rate the ease of using tablets to place your orders? | Scaled | 1. very easy | 2. somewhat easy | 3. neither easy nor difficult | 4. somewhat difficult | 5. very difficult
|  |  | would you return again this month? | Yes/No | YES | NO | MAYBE
a check out time under 1 min | is the goal being met and what are the lessons learned | check out time | how likely would the customer recommend our restaurant to a friend? | Multiple choice | 1. very likely | 2. somewhat likely | 3. would not recommend
|  |  | was the customer check out time one minute or under? | Yes/No | YES | NO
|  |  | did the tablet help you get better checkout time? | True/False | TRUE | FALSE
|  |  | how satisfied is the customer with the time check out time? | Multiple choice | 1: Very Satisfied | 2: Somewhat satisfied | 3: Neither satisfied nor dissatisfied | 4: Somewhat dissatisfied | 5: Very dissatisfied
average rate of technical issues reported by customers be less than 5% in the first six months | what are the most common participant reactions | rate of technical issue reported | did the customer encounter any technical difficulties? | Yes/No | YES | NO
|  |  | how bad was the difficulty? | Multiple choice | 1. very bad | 2. modetrate | 3. minor difficulty | 4. negligable
100% order accuracy | what is working and whats not working? | order accuracy | how would the guest rate the time that took to move around the technical problem? | Scaled | 1. no time at all | 2. not much and we waited | 3. not much and we had to use another method | 4. too long but we waited | 5. too long and had to use another method
|  |  | how would the customer rate the accuracy of your order? | Multiple choice | 1. very accurate | 2. somewhat accurate | 3. completely wrong
|  |  | what would your suggest ions be to better get your order the next time? | Open-ended
ten minute-or-less wait time for a table | is the goal being met and how can we improve? | wait time for a table | how long did the guest have to get a table? | Multiple choice | 1. no time at all | 2. less than two minutes | 3. around five minutes | 4. 5-10 minutes | 5. more than 10 minutes